NPAPA Improvement Plan

|  | Action | Timescale | Lead Officer |
| --- | --- | --- | --- |
| Engagement with Stakeholders 12.2 Review engagement with non-statutory stakeholders on strategy and policy development and consider the timing of consultations, how feedback is provided, and how engagement is maintained. [4.6] 12.5 Review the process for involving customers, stakeholders, staff and communities in annual priority setting. [5.6] 12.6 Undertake routine surveys, information and intelligence gathering exercises for all relevant stakeholders and Broads communities. [5.7] 12.8 12.9 Manage the perceptions that the focus on conservation has been lessened. [6.7] 12.13 Increase dialogue, break down barriers and build trust between local navigation interests and the Authority. [7.15] 12.14 Improve engagement and two way exchanges with local communities and groups. [8.10] 12.17 Undertake the agreed review of governance and consultative structures. [9.10] 12.21 As part of the review of consultative structures determine the arrangements for engaging with key stakeholders including the role of the Broads Forum. [10.9 & 9.12] | Undertake the agreed review of governance and consultative arrangements including consultation on strategy and policy development, annual priority setting, performance indicators, surveys of opinion and the role of the Broads Forum, Parish Forums and Pop-Ins with the aim of improving the Authority’s engagement with non-statutory stakeholders and local communities. Strengthen the Authority’s existing network of biodiversity relationships to build a greater understanding of our work. A major Broads’ conference has already been planned by the Authority for February 2012 on World Wetlands Day to bring together the major partners to foster a landscape scale approach and cooperative working. Following the productive meeting with the RYA and BMF seek regular meetings with the Norfolk and Suffolk Boating Association and the Broads Hire Boat Federation to increase the dialogue with the two organisations, break down any barriers and build trust. Identify relationship managers for all the key stakeholder organisations. | The report to the Authority in November contained a timetable for the Governance Review that concluded with a report to the Authority in July 2012. Broads conference on 2 February 2012 Contact NSBA and BHBF in February February 2012 | Director of Planning and Strategy Senior Ecologist Chief Executive Management Team |
| Branding of Partnership Projects 12.3 Review how decisions are made on the branding of projects and how the profile of all partners can be appropriately maintained. [4.8] | Agree with partners during the initiation stage how projects are to be branded. | On-going | Head of Strategy and Projects |
| National Park Status 12.4 Establish a Member/stakeholder structure to establish a common understanding on the basis for progressing national park status. [4.9] | Establish Member/Stakeholder Working Group to progress national park status, when the Governance and Tolls Reviews, have been completed. Report to the Authority on the suggested composition of the Working Group, | September 2012 | Chief Executive |
| Target Setting 12.7 Include more outcome focused and measurable targets and milestones in strategy and other priority lists. [5.8] 12.8 Set clearer targets with delivery outcomes for nature conservation work and communicate the resulting improvements more widely to help inform external audiences. [6.6] | As part of the annual process of setting targets ensure they are in line with the adopted Broads Plan and where appropriate outcome focused. Draft Strategic Priorities on this agenda proposing consultation with the Broads Forum & Navigation Committee. Continue to communicate the benefits of the work undertaken to the relevant audiences. | February 2012 On-going | Head of Governance and Executive Assistant Communications Manager |
| Tourism 12.10 Examine options for future tourism funding that might help maintain the enviable relationship which the Authority has with the tourism sector. [7.12] 12.11 Review the scope for further joint working and coordination of activities on understanding and enjoyment issues. [7.13] | The Authority’s European partnership project Sustainable Tourism in Estuarine Parks (STEP) comes to an end in December 2012. Six months before BA staff funding ceases, review the different funding options to allow the Authority’s work on tourism to continue and the scope for further joint working with other tourism stakeholders. Report to the Authority setting out the options. | September 2012 | Head of Strategy and Projects |
| Dredging and Mooring Targets 12.12 Establish a framework that provides a route to discuss differences of view on navigation outcomes. [7.14] | Prepare a report for discussion at the Navigation Committee on the outcome measures for dredging and moorings. | Navigation Committee in April 2012 | Sr.Waterways & Recreation. Officer |
| Volunteers 12.15 Introduce measures to maintain the motivation and enthusiasm of volunteers at a time of change. [8.11] | Implementation of the Volunteer Strategy, the Volunteer Handbook and Policy that the Authority will deliver a motivated and enthusiastic volunteer service. | On-going | Volunteer Coordinator |
| Performance Management 12.16 Review whether the arrangements for monitoring and reporting on performance are effective and appropriate in the new organisational structure. [9.9] | The Management Team has reviewed the need for a nominated officer to be responsible for performance management and concluded that the present arrangement, whereby the whole Team has a collective responsibility, is preferable. | None | None |
| Role of Members 12.18 Review the role of Members in engaging with the wider community including their possible use in advocacy, ambassadorial and information gathering roles. [9.11] | Broads Authority Chairman to review with Members in their annual appraisals the scope for them to be more involved in delivering advocacy, ambassadorial and information gathering roles. | Completion of the appraisals by the end of May 2012 | Chairman |
| Equalities 12.19 Progress the implementing of equalities issues. [9.13] | Progress the implementation of equalities issues, including the review and updating of the Equality Policy, provision of training for staff and members and, through the establishment of an Equalities Working Group, achieve Level 1 (Developing) of the Equality Framework for Local Government, with a view to progressing to Level 2 (Achieving) during 2013/14. | Target date for achieving Level 1 by 31st March 2013 and then move on to looking to achieve Level 2 | Head of Human Resources |
| Organisational Change 12.20 As the benefits of the organisational change become embedded, consider when the appropriate time may be to relax organisational constraints and allow the skills, knowledge and innovation of staff to be used more fluidly. [10.8] | The Authority will continue to use the Staff Representative Group, regular Team meetings and monthly 1:1s to identify any issues of concern and encourage opportunities for empowering staff and facilitating innovation within the new work structure, processes and guidelines. | On-going | Management Team and Management Forum |